## 12-Month Roadmap
🚀 AKSH HEALTH UK/EUROPE — 12-MONTH EXECUTION ROADMAP (M1-M12)
April 2026 - March 2027 ¦ Budget: £1,180K ¦ Team Size: 18 FTE
Month | Phase | Primary Deliverable | Owner | Budget (£K) | Team | Validation Gate | Status
M1 (Apr 26) | 1A | AWS EKS + FHIR PoC + CSO Hire | CTO + CEO | 48 | 6 | Infrastructure ready + CSO onboard | 🔴 CRITICAL
M2 (May 26) | 1B | SYNTHESIS + DrASSIST Agents (LangGraph) | AI/ML + Frontend | 36 | 8 | 50 synthetic encounters processed | Planned
M3 (Jun 26) | 1C | Voice Layer + JSL NLP Integration | Frontend + AI/ML | 42 | 8 | Voice SOAP generation <3.5min | Planned
M4 (Jul 26) | 1D | SHIELD + EQUITY Agents + Graph DB | AI/ML + CSO | 40 | 8 | Safety validation 0 missed alerts | Planned
M5 (Aug 26) | 1E | Phase 1 Validation Complete | QA + Clinical | 30 | 6 | DrASSIST F1≥0.82, Triage accuracy ≥90% | Planned
M6 (Sep 26) | 1F | DCB0129 Safety Case Draft + NHS Partners Engaged | CSO + CEO | 38 | 6 | DTAC pre-submission approved | Planned
M7 (Oct 26) | 2A | EMIS Web Integration + 3 GP Pilot Sites Selected | CTO + NHS BD | 52 | 8 | EMIS sandbox testing passed | Planned
M8 (Nov 26) | 2B | VOICE Agent (Ambient Docs) + SystmOne prep | AI/ML + Frontend | 44 | 8 | SOAP auto-generation >85% accuracy | Planned
M9 (Dec 26) | 2C | IntelliProve Integration + Mental Health Bundle | Frontend + Product | 32 | 6 | Biomarker FHIR schema validated | Planned
M10 (Jan 27) | 2D | 3 ICS Pilots Launch + ORACLE Agent MVP | NHS BD + AI/ML | 56 | 10 | 150 clinicians trained, 5K patients | Planned
M11 (Feb 27) | 2E | Federated Learning Architecture + RWE pipeline | AI/ML + DevOps | 48 | 8 | 3-node model design approved | Planned
M12 (Mar 27) | 2F | DCB0129 Safety Case Submission Ready + NHS App prep | CSO + CTO | 54 | 8 | DTAC approval + MHRA pathway open | Planned

## Critical Path
🔴 CRITICAL PATH — M1-M12 Programme Blockers
Timeline | Priority | Blocker | Owner | Impact if Missed
Week 1 (Apr 1) | 🔴 CRITICAL | Hire Clinical Safety Officer (GMC/NMC/GPhC registered) | CEO | No CSO = entire programme blocked by DCB0129 requirement
Week 2 (Apr 8) | 🔴 CRITICAL | Apply to EMIS Web Partner Programme | CTO | 3-4 month pipeline; delay blocks M7 EMIS integration
Week 3 (Apr 15) | 🔴 CRITICAL | Engage DTAC/DCB0129 regulatory consultant (£120K/yr) | CEO | Missed engagement = 6 month regulatory delay
Week 4 (Apr 22) | 🟠 HIGH | AWS EKS London setup + load 100 Synthea patients | CTO | Foundation for all downstream agents
M2 (May 1) | 🟠 HIGH | LangGraph SYNTHESIS agent operational | AI/ML Lead | Blocks DrASSIST, SHIELD, ORACLE agents
M2 (May 15) | 🟠 HIGH | John Snow Labs NLP license signed | CEO | 8-week integration cycle; delays clinical accuracy M4
M3 (Jun 1) | 🟠 HIGH | Deepgram Medical ASR + ElevenLabs TTS integrated | Frontend | Blocks voice-first workflows M3-M4
M4 (Jul 1) | 🟠 HIGH | Neo4j + Weaviate knowledge graph schema validated | AI/ML Lead | Foundations for ORACLE, federated learning M11
M5 (Aug 15) | 🟡 MEDIUM | Phase 1 validation gates passed (F1≥0.82, safety 0 missed) | QA Lead | Gates Series A evidence; remediation = 4 weeks
M6 (Sep 15) | 🟡 MEDIUM | DCB0129 Hazard Log complete for DTAC pre-submission | CSO | Missed = 2 month regulatory slip M6→M8
M7 (Oct 1) | 🟠 HIGH | EMIS Web API sandbox testing passed (vendor approval) | CTO | Blocks GP practice integration M7-M8
M10 (Jan 15) | 🟠 HIGH | 3 ICS pilot sites fully trained & live with real patients | NHS BD | Real-world data validation; blocks scale-up M16
M12 (Mar 1) | 🔴 CRITICAL | DCB0129 Safety Case submission ready (500+ page dossier) | CSO | Miss = MHRA pathway delayed 6 months

## M1 Weekly Detail
🗓️ M1 (APRIL 2026) — Week-by-Week Critical Path
Week | Day | Deliverable | Owner | Done When...
Week 1 Apr 1-5 | Day 1 | CSO Job Spec Finalized + RCGP reach-out begins | CEO | 1 candidate identified
Week 1 Apr 1-5 | Day 2 | EMIS Web Partner Programme application submitted | CTO | Formal acknowledgment from EMIS
Week 1 Apr 1-5 | Day 3 | DTAC/DCB0129 Regulatory Consultant engaged (signed contract) | CEO | Consultant on-boarded, kickoff call
Week 1 Apr 1-5 | Day 4 | AWS London EKS cluster creation + RDS setup | CTO + DevOps | Cluster accessible, security groups HIPAA-ready
Week 1 Apr 1-5 | Day 5 | 100 Synthea patient records loaded to test data lake | DevOps + QA | Data ingestion validated
Week 2 Apr 8-12 | Day 6 | Medplum FHIR server deployed on EKS (sandbox) | CTO + AI/ML | FHIR /Patient and /Observation endpoints live
Week 2 Apr 8-12 | Day 7-8 | LangGraph SYNTHESIS agent skeleton + Claude Sonnet 4 integration | AI/ML Lead | Agents repo ready for M2 sprint
Week 2 Apr 8-12 | Day 9 | CSO final interview round (target hire by end of week) | CEO + CTO | Offer extended to selected candidate
Week 3 Apr 15-19 | Day 10 | SYNTHESIS agent: voice input → FHIR Observation creation | AI/ML + Frontend | End-to-end flow POC (10 test cases)
Week 3 Apr 15-19 | Day 11 | Hazard Log template created per IEC 62304 | CSO + Reg Consultant | v0.1 Hazard Log framework
Week 3 Apr 15-19 | Day 12 | EMIS Web API sandbox access confirmed | CTO | Credentials received, documentation reviewed
Week 4 Apr 22-26 | Day 13 | CSO onboarded + safety committee established | CSO + CEO | First safety review board meeting scheduled
Week 4 Apr 22-26 | Day 14 | SYNTHESIS agent: FHIR → SOAP note generation | AI/ML | SOAP template + CDS Hooks integration ready M2
Week 4 Apr 22-26 | Day 15 | Deepgram Medical API + ElevenLabs TTS contracts signed | Product | API keys provisioned, sandbox access live

## 12-Month Budget
💰 12-MONTH BUDGET ALLOCATION (£1,180K total)
Category | Item | Total (£K) | Months | Monthly (£K)
Personnel | Engineering (5 FTE) | 180 | 12 | 15
Personnel | AI/ML (3 FTE) | 108 | 12 | 9
Personnel | Frontend (2 FTE) | 48 | 12 | 4
Personnel | DevOps + QA (2 FTE) | 48 | 12 | 4
Personnel | CSO / Clinical (1 FTE) | 60 | 12 | 5
Personnel | NHS Business Dev (1 FTE) | 48 | 12 | 4
Regulatory | DCB0129 + DTAC Consultant | 120 | 1 | 10
Regulatory | ISO 27001 + DSPT compliance | 48 | 1 | 4
Cloud | AWS EKS + RDS London | 120 | 12 | 10
Cloud | Data egress + backup | 24 | 12 | 2
APIs & Licenses | John Snow Labs NLP (annual) | 48 | 1 | 4
APIs & Licenses | Deepgram Medical ASR | 24 | 12 | 2
APIs & Licenses | ElevenLabs TTS | 18 | 12 | 1.5
APIs & Licenses | Claude API + GPT-4.1 | 42 | 12 | 3.5
Infrastructure | Neo4j Enterprise | 36 | 12 | 3
Infrastructure | Weaviate Cloud | 24 | 12 | 2
Infrastructure | Mirth Connect licensing | 12 | 12 | 1
Clinical | 3 GP Pilot sites (training + support) | 60 | 1 | 5
Clinical | Phase 1 validation studies | 30 | 1 | 2.5
Commercial | EMIS + SystmOne partner engagement | 36 | 1 | 3
Contingency | Risk buffer (10%) | 118 | 1 | 10
TOTAL 12-MONTH BUDGET |  | 1252